`

Facilitator: JoAnne Malloy Note Taker: Cat Jones

Time Keeper: Norm Checker:

Present: JoAnne Malloy, Cat Jones, Shawn Blakey, Dianne Castrucci, Nilufer Isvan, Hannah Raiche, Paul Kiernan

**Agenda**

1. Re-orient to task, workplan, mission and membership (10 min)
2. Pilot site ramp ups and timelines - Learning Collaborative and 7 Challenges training (30 min)
3. Higher Education update - possibility of cross institution work (30 min)
4. Policy committee update - MAT and family and youth peer support (20 min)

| Item | Discussion | Action Items | Who | When |
| --- | --- | --- | --- | --- |
| Updates | FY2019 is ending soon – please get your invoices to IOD  Pilot Site – Greater Nashua Mental Health Center | Send invoices to JoAnne Malloy & Jenn Donahue – [jennifer.donahue@unh.edu](mailto:jennifer.donahue@unh.edu) | JSI, Youth MOVE, NHTIAD | asap |
| Updates to Goals/ Timelines | Ensure pilot sites are administering and inputting CANS data  Who provides SBIRT training to providers in site areas?  Connect w/ Doorways in each pilot region so they know about Creating Connections NH Community of Practice  June 20, 9-12  July 17 – TOPIC: CANS training; Wraparound (What is it? Who is a good candidate?) - Daryll  Aug 1, 10:30-12:30 (before IAC meeting)  Sept 12, 9-12  Oct 10, 9-12  Nov 21, 9-12  Dec 12, 9-12  Agenda for 6/20:  Introductions  What is a Community of Practice? – Rekha/Addie, 15 mins  Mission, Norms – Rekha, 20 mins  Model/Seven Challenges – Shawn  Treatment & Recovery Continuum – JoAnne  Data Collection – Nilufer  Peer Support Overview – Youth MOVE  Seven Challenges new dates: July 24-26, 2019  Training announcements, registration – Dianne  People who w8ill not need training materials: Daryll, Shawn, Adele, JoAnne, Youth MOVE, Paul  Training materials: GNMHC, site #2  Seven Challenges Leadership Training: October 2019, date TBA  Can/should pilot sites begin accepting referrals and providing services prior to completing training in EBPs?  Work w/ each site to create an individualized rollout plan?  Courses/certificate program – UNH (social work, OT, family studies) wrote a proposal for HRSA grant. Opioid Use Disorder focus.  What is currently out there and how are they recruiting? – SNHU, MH counseling, Rivier, KSC, GSC, MCC, PSU, etc. | CANS to Nilufer  Ask Jill Burke  Set up CoP  Check dates w/ Rekha  Agenda for 6/20 (incl. Nilufer, data collection, 60-90 mins)  Dianne will need official contact info for each pilot site  Dianne will need list of non-pilot-site attendees  Discuss w/ Adele and Erica  Survey? JoAnne will discuss with Brian Miller | Shawn  Shawn  JoAnne, Shawn  Paul  Shawn | Summer |
|  |  |  |  |  |

**Next meetings:**

* **Workforce Group – June 17, 1-3, at IOD Concord**
* **Workforce Group – July 8, 1-3:30, at NHADACA, 130 Pembroke Road Concord**
* **Inter-Agency Council – June 6, 1-3, at IOD Concord**