Facilitator: JoAnne Malloy Note Taker: Cat Jones

Time Keeper: Norm Checker:

Present: JoAnne Malloy, Cat Jones, Nilufer Isvan, Rekha Sreedhara, Adele Bauman, Paul Kiernan, Dianne Castrucci

**Agenda**

1. Updates
2. Review workplan

| **Item** | **Discussion** | **Action Items** | **Who** | **By When** |
| --- | --- | --- | --- | --- |
| Updates | * JoAnne is working on finalizing a FY21 contract w/ Youth MOVE
* 38 youth enrolled
* IOD research assistant is converting Seven Challenges journals to fillable PDFs
* JSI has submitted two contract proposals, one for TA and one for data & eval
* Still waiting to hear about HRSA grant proposal that was submitted in April
 | Will it work on a smartphone? |  |  |
| Review workplan | * Upcoming Seven C. site visit to Nashua
* Shawn and JoAnne are hoping to train more people in Seven Challenges
* UNH Extension has created stackable “mini credentials” – JoAnne is meeting with them this week
* SUD residential contracts to go out – target October 2021. BCBH created levels of care system with 5 levels.
* ECC practice profile has been on hold due to Covid
* Peer to peer support work is progressing. Target: APGs up and running by fall (possibly virtually).
* Treatment locator updates – ownership has been transferred to BDAS as of June 30
* Revision of Medicaid rules to support Seven Challenges work. ASAM is required for 6 hours/week. If 9 hours required it should be more flexible.
 | Looking for $$Follow up after callOn holdDiscuss w/ MCOs | JoAnneAdele - Paul can help too |  |

**Next meetings:**

* **Workforce Group –** August 17, 2020, 1-2pm, Zoom
* **Peer Support –** TBD
* **Alternative Peer Groups (APGs) Subcommittee –** July 23, 2020, 9-10:30am
* **Interagency Council –**
* **Community of Practice –** August 19, 2020, 11-1pm